## Sheet1
Phase 3 - Neelam Appliances | [5 empty] | BackEnd |  |  |  | FrontEnd |  |  |  | Report | Project Start Date | 2024-05-01 |  | Dead Line | 2024-08-01
No | MASTER MODULE | Developer Status | Task Name | Backend Developer | FrontEnd Developer | Start Date | End Date | Total Days | Backend Status | Start Date | End Date | Total Days | Frontend Status | Test Status | Current Date | 2024-07-19 | 79 | Days Remaining | 13
1 | Manufacturing/Production
1.1 | Purchase of Raw Material | COMPLETED | In jobwork | Omkar | Anish |  |  |  | COMPLETED |  |  |  |  | DONE
1.2 | Stage 1 – Cutting | COMPLETED | In jobwork | Omkar | Nihal |  |  |  | COMPLETED |  |  |  |  | DONE
1.3 | Stage 2 – Moulding/Shaping | COMPLETED | In jobwork | Omkar | Nihal |  |  |  | COMPLETED |  |  |  |  | DONE
1.4 | Stage 3 – Polishing | COMPLETED | In jobwork | Omkar | Nihal |  |  |  | COMPLETED |  |  |  |  | DONE
1.5 | Stage 4 - Quality check | COMPLETED | In jobwork | Omkar | Nihal |  |  |  | COMPLETED |  |  |  |  | DONE
2 | Assembly
2.2 | Set Barcode
2 | TASK NAME
2.2.1 | Added fields in index pages also in add entries | COMPLETED | CRUD operation | Sahil | Anish |  |  |  | COMPLETED |  |  |  | COMPLETED
2.2.1 | Created Database to store data | COMPLETED | CRUD operation | Sahil | Anish
2 | ISSUES
2 | Master Cartoon | Completed | CRUD operation | Sahil | Nihal |  |  |  | COMPLETED |  |  |  | COMPLETED | COMPLETED
2.4 | Cartoon Barcode | Completed | CRUD operation | Sahil | Nihal |  |  |  | COMPLETED |  |  |  | COMPLETED | COMPLETED
2.5 | Standard Lable packaging | Completed | CRUD operation | Sahil | Nihal |  |  |  | COMPLETED |  |  |  | COMPLETED | COMPLETED
2.7 | Repackaging | Completed | CRUD operation | Sahil | Anish | 2024-06-17 | 2024-06-18 |  | COMPLETED | 2024-06-17 | 2024-06-18 |  | COMPLETED | COMPLETED
2.8 | Loose Packing | COMPLETED | Developed done | Sahil | Anish | 2024-06-14 | 2024-06-14 |  | COMPLETED | 2024-06-17 | 2024-06-18 |  |  | COMPLETED
2.8.1 | Changes --> New approval for new module | COMPLETED | CRUD operation | Sahil | Anish | 2024-06-14 | 2024-06-15 |  | COMPLETED | 2024-06-17 | 2024-06-18 |  |  | COMPLETED
2.9 | Product Barcode | Backend done | CRUD operation | Sahil | Anish |  |  |  | COMPLETED |  |  |  | COMPLETED | COMPLETED
3 | Grouping(For reporting purpose) |  | Need Discussion
3 | Design of Grouping | COMPLETED |  | Sahil | Anish |  |  |  | COMPLETED | 2024-06-12 | 2024-06-12 |  | COMPLETED | COMPLETED
3.1 | Grouping CRUD as per Excel Group 10 | COMPLETED |  | Sahil | Anish | 2024-06-20 | 2024-06-25 |  | COMPLETED | 2024-06-26 | 2024-06-27 |  | COMPLETED | COMPLETED
3.3 | CRUD in 10 groups | COMPLETED |  | Sahil | Anish | 2024-06-20 | 2024-06-22 |  | COMPLETED | 2024-06-20 | 2024-06-22 |  | COMPLETED | COMPLETED
3.4 | Pagination | COMPLETED |  | Sahil | Anish | 2024-06-26 | 2024-06-27 |  | COMPLETED | 2024-06-26 | 2024-06-27 |  | COMPLETED | COMPLETED
3 | ISSUES
4.) | Bill of Material | COMPLETED |  | Kaustubh sir | Anish |  |  |  | COMPLETED |  |  |  | COMPLETED | DONE
4 | Submit Navigation | COMPLETED | [6 empty] | IN PROCESS | 2024-06-17 | 2024-06-17
5.) | Delivery Challan | [7 empty] | COMPLETED |  |  |  | COMPLETED | DONE
5.1 | Converted from sales order | COMPLETED |  | Omkar | Anish |  |  |  | COMPLETED |  |  |  | COMPLETED | DONE
5.2 | Direct DC | COMPLETED |  | Omkar | Anish |  |  |  | COMPLETED |  |  |  | COMPLETED | DONE
5.3 | Pending from sales order | COMPLETED |  | Omkar | Anish |  |  |  | COMPLETED |  |  |  | COMPLETED | DONE
6.) | Signature in Print | phase 4 | Need discuss |  | Not Assigned
7.) | Download & Print | testing pending |  | Not Assigned | Not Assigned | PDF OR EXCEL
8.) | Text SMS | PENDING |  | Not Assigned | Not Assigned | Reminder
9.) | Distributor Sales Return
9.1 | CRUD Done | COMPLETED |  | Omkar | Anish | 2024-07-01 | 2024-07-02 |  | COMPLETED | 2024-07-02 | 2024-07-02 |  | COMPLETED | DONE
9.2 | Report Effects pending | COMPLETED |  | Omkar | Anish | 2024-07-01 | 2024-07-02 |  | COMPLETED | 2024-07-02 | 2024-07-02 |  | COMPLETED | DONE
10.) | Product Type |  |  | Not Assigned | Not Assigned
10.1 | Raw Material | COMPLETED | Added field | Omkar | Not Sure |  |  |  | COMPLETED |  |  |  | COMPLETED | DONE
10.2 | Semi-Finished Goods | COMPLETED | Added field | Omkar | Not Sure |  |  |  | COMPLETED |  |  |  | COMPLETED | DONE
10.3 | Finished Goods | COMPLETED | Added field | Omkar | Not Sure |  |  |  | COMPLETED |  |  |  | COMPLETED | DONE
11.) | Staff Asset Management | IN PROCESS |  | Sahil | Anish | 2024-05-31 | Not Sure |  | IN PROCESS
11.1 | Asset Master(CRUD) | COMPLETED | Sir Testing pending | Sahil | Anish | 2024-05-31 | Not Sure |  | COMPLETED | 2024-05-29 | Not Sure |  | IN PROCESS | DONE
11.2 | Asset Request Form | COMPLETED | Sir Testing pending | Sahil | Anish | 31-06-2024 | 2024-06-04 |  | COMPLETED | 31-06-2024 | 2024-06-04 |  | IN PROCESS | DONE
11.3 | Assign to Staff | COMPLETED | Sir Testing pending | Sahil | Anish | 31-06-2024 | 2024-06-04 |  | COMPLETED | 31-06-2024 | 2024-06-04 |  |  | DONE
11 | Reports | IN PROCESS
PENDING
PENDING
PENDING
12.) | Contract Mangement | COMPLETED | Testing pending | Omkar | Anish | 2024-06-12 | 2024-06-13 |  | COMPLETED | 2024-06-12 |  |  | COMPLETED | DONE
12.1 | Contract Mgmt image update | COMPLETED |  | Omkar | [9 empty] | DONE
12.2 | Contract Report | COMPLETED |  | Omkar | Nihal | 2024-07-09 | 2024-07-10 |  | COMPLETED | 2024-07-09 | 2024-07-10 |  | COMPLETED | DONE
13.) | Projection | PENDING | Need Discuss | Omkar | Anish
14.) | Projection Report | PENDING | backend | Omkar | Anish | 2024-05-31 | Not Assigned |  | In process | 2024-05-31 |  |  | Not Assigned
15.) | Retailer Without Distributor & Direct Customer |  |  | Anish | Omkar |  |  |  | Complete |  |  |  | Complete | DONE
15.1 | Secondary Order without Distributor/direct customer | COMPLETED |  | Anish | Omkar |  |  |  | Complete |  |  |  | Complete | DONE
15.2 | Sales order will convert | COMPLETED |  | Anish | Omkar |  |  |  | Complete |  |  |  | Complete | DONE
15.2 | Delivery challan will convert | COMPLETED |  | Anish | Omkar |  |  |  | Complete |  |  |  | Complete | DONE
15.3 | Tax Invoice will convert | COMPLETED
15.4 | Reports for Customer without Distributor | COMPLETED
16 | E-Invoicing(Format) |  | Design as shared | [6 empty] | 2024-07-18 | 2024-07-18 |  | IN PROCESS
17 | E-way Bill(Tax Invoice)
17.1 | Tax Invoice | IN PROCESS
17.2 | E-Invoice
17 | Sales Return/Credit Note | IN PROCESS |  | Chitaranjan | Anish | 2024-07-09 | 2024-07-09 |  | COMPLETED |  |  |  | IN PROCESS
17 | Purchase Return/Debit Note | IN PROCESS |  | Chitaranjan |  | 2024-07-13 | 2024-07-17 |  | COMPLETED |  |  |  | IN PROCESS
17.3 | Qr Code generating after invoice | COMPLETED |  | Chitaranjan | Anish | 2024-06-12 | 2024-06-12 |  | COMPLETED | 2024-06-12 | 2024-06-12 |  | IN PROCESS
18 | GST Sales E-invoice | COMPLETED |  | Chitaranjan | Anish | 2024-07-09 | 2024-07-12 |  | COMPLETED | 2024-07-09 | 2024-07-12 |  | COMPLETED | Pending
18 | Through neelam user/pass for authentication & generating invoice | IN PROCESS
17.3 | E-way Bill(Part A & part B)
TASK
17.3.1 | Generate E-way along with E-invoice bill | IN PROCESS |  | Chitaranjan | Anish | 2024-05-30 | 2024-06-13 | -14 | COMPLETED | 2024-05-06 | Not Sure |  | IN PROCESS
17.3.2 | E-way bill through IRN No | IN PROCESS |  | Chitaranjan | Anish | 2024-05-30 | 2024-06-13 | -14 | COMPLETED | 2024-05-06 | Not Sure |  | IN PROCESS
17.3.3 | Get E-way Bill Through IRN | IN PROCESS |  | Chitaranjan | Anish | 2024-05-30 | 2024-06-13 | -14 | COMPLETED | 2024-05-06 | Not Sure |  | IN PROCESS
18.3 | PART B
18.3.1 | E-way Bill generate | IN PROCESS |  | Chitaranjan | Nihal | 2024-05-30 | 2024-06-13 | -14 | COMPLETED | 2024-07-19 | 2024-07-19 |  | COMPLETED | Pending
18.3.2 | E-way Bill Authentication | COMPLETED |  | Chitaranjan | Nihal | 2024-05-30 | 2024-06-13 | -14 | COMPLETED | 2024-07-19 | 2024-07-21 |  | COMPLETED
18 | ISSUES
18 | Solving GST class problems while uploading server. | COMPLETED | BACKEND ONLY | Chitaranjan |  | 2024-07-25 |  |  | COMPLETED
18 | Uploading on local server | COMPLETED |  | Chitaranjan |  |  |  |  | COMPLETED
18 | GST Reducing Sales Fields | COMPLETED |  | Chitaranjan |  | 2024-07-06 | 2024-07-09 |  | COMPLETED
19 | E-way(Job Work)
19.1 | JobWork | Completed | Testing pending | Chitaranjan | Anish |  |  |  | COMPLETED | 2024-05-29 | 2024-05-29 |  |  | Completed
19.2 | Delivery Note | IN PROCESS |  | Chitaranjan | Nihal | 2024-07-20 | 2024-07-23 |  | COMPLETED | 2024-07-23 | 2024-07-23 |  | COMPLETED
20 | GST Master Details Fetching | COMPLETED | In E-way bill | Chitaranjan | Not Assigned |  |  |  | COMPLETED | 2024-05-22 | 2024-05-28
21 | New Requirement till phase 2
21.1 | Permission Right | phase 4
21.2 | Minutes of Meeting | COMPLETED | Minutes | OMKAR | Nihal | 2024-06-05 | 2024-05-07 |  | Completed | 2024-05-09 | Not Sure |  | Completed | Completed
21 | TASK
21 | Minutes of meeting update | COMPLETED | Minutes | OMKAR | Nihal | 2024-06-15 | 2024-06-15 |  | Completed | 2024-06-15 | 2024-06-15 |  | Completed | Completed
21 | ISSUES | COMPLETED
21.3 | The Account Icon | COMPLETED |  |  | anish |  |  |  |  | 2024-06-20 | 2024-06-20 |  | COMPLETED | DONE
21.4 | Excel Import | not possible
21.5 | Master Grouping | COMPLETED |  | Sahil | anish | 2024-06-20 | 2024-06-25 |  | COMPLETED
21.6 | Changes of retailer & distributor | COMPLETED |  | Omkar | Anish | 2024-05-17 | 2024-05-23 |  | COMPLETED | 2024-05-17 | 2024-05-23 |  |  | DONE
21.7 | Secondary order Print | COMPLETED |  | Omkar | Anish | 2024-05-17 | 2024-05-23 |  | COMPLETED | 2024-05-17 | 2024-05-23 |  |  | DONE
21.8 | Order Value | COMPLETED |  | Omkar | Anish | 2024-05-17 | 2024-05-23 |  | COMPLETED | 2024-05-17 | 2024-05-23 |  |  | DONE
21.9 | Distributor Opening Stock | COMPLETED |  | Omkar | Anish | 2024-05-17 | 2024-05-23 |  | COMPLETED | 2024-05-17 | 2024-05-23 |  |  | DONE
21.1 | Order Report | COMPLETED |  | Omkar | Anish | 2024-05-17 | 2024-05-23 |  | COMPLETED | 2024-05-17 | 2024-05-23 |  |  | DONE
21.11 | Invoice Attachment for Distributor | COMPLETED |  | Omkar | Anish | 2024-05-17 | 2024-05-23 |  | COMPLETED | 2024-05-17 | 2024-05-23 |  |  | DONE
21.12 | Tax invoice upload | COMPLETED |  | Omkar | Anish | 2024-05-17 | 2024-05-23 |  | COMPLETED | 2024-05-17 | 2024-05-23 |  |  | DONE
21.13 | Distributor minimum stock | COMPLETED |  | Omkar | Nihal | 2024-06-05 | Not Sure |  | COMPLETED | 2024-06-05 | Not Sure |  | COMPLETED | DONE
21.14 | Distributor Minimum Stock Report | COMPLETED |  | Omkar | Nihal | 2024-06-05 | Not Sure |  | COMPLETED | 2024-06-05 | Not Sure |  | COMPLETED | DONE
21.16 | Text Colour | phase 4
21.17 | Time Line for Check In/out | COMPLETED |  | Nihal
21.18 | Revision in Product Master | COMPLETED |  | need discuss | Not Assigned
21.19 | Play Store | phase 4 |  | need discuss | Not Assigned
21.2 | Supplier Multiple Address | COMPLETED | Testing pending | Omkar | Nihal
21.21 | Shipping Address Master | COMPLETED | Testing pending | Omkar | Nihal
21.22 | Distributor Outward Stock | COMPLETED
21.23 | Distributor with Retailer Stock Outward | COMPLETED
21.24 | Brand wise Ean Code and details maintain | IN PROCESS | Testing pending | Sahil | Anish
22 | Changes in Mobile Application
22.1 | Standard Attendance | COMPLETED |  | Sahil | Anish | 2024-05-22 | Not Sure |  | COMPLETE |  |  |  | COMPLETE
22.2 | Timeline | COMPLETED |  | Omkar | Nihal |  |  |  | COMPLETE |  |  |  | COMPLETE | DONE
22 | Optimization in map Module | COMPLETED |  | No Backend | Nihal |  |  |  |  | 2024-07-23 | 2024-07-23 |  | IN PROCESS
22.3 | Mobile Catalogue | COMPLETED |  | No Backend | Nihal |  |  |  | COMPLETE |  |  |  | COMPLETE | DONE
22.4 | Scheme launch | COMPLETED |  | No Backend | Nihal | [7 empty] | COMPLETE | DONE
22.5 | Dashboard Redirect Link | pending |  | Not Assigned | Nihal
22.6 | Sales staff expense claim report format | need discuss | As per parin format | Not Assigned | Nihal | Discuss
22.7 | Notification icon time feature
22.7.1 | FireBase/Expo notification Features | COMPLETED |  | Chitaranjan | Nihal | 2024-06-17 | 2024-07-01 |  | COMPLETE | 2024-06-17 | 2024-07-01 |  | COMPLETE | COMPLETE
22.8 | SMS otp is required for mobile | pending |  | Not Assigned | Not Assigned
22.9 | Email Verify compulsion | COMPLETED |  | Sahil | Nihal | 2024-06-17 | 2024-06-17 |  | COMPLETED | 2024-06-17 | 2024-06-17 |  | COMPLETE | COMPLETE
27 | Extras Mobile app
27.1 | Back button--> Navigation steps as per user steps | COMPLETED |  | Omkar | Nihal | 2024-06-08 | 2024-06-11 |  | Completed | 2024-06-08 | 2024-06-11 |  | Completed | Done
27.2 | In Your cart items--> Confirmation Alerts | COMPLETED |  | Omkar | Nihal | 2024-06-11 | 2024-06-11 |  | Completed | 2024-06-11 | 2024-06-11 |  | Completed | Done
27.3 | Recreated the attendance | COMPLETED |  | Omkar | Nihal | 2024-06-11 | 2024-06-11 |  | Completed | 2024-06-11 | 2024-06-11 |  | Completed | Done
27.4 | Map Speed increase | COMPLETED |  | Omkar | Nihal | 2024-06-11 | 2024-06-11 |  | Completed | 2024-06-11 | 2024-06-11 |  | Completed | Done
27.5 | Download image option product of month | COMPLETED |  | done | Nihal
27 | Errors In Mobile app
1 | exbo notification app cut button. | COMPLETED
23 | Extras Development not included in drafting - Committed
23.1 | all index pages need showing of 200 line rows |  | YES |  | Nihal
24 | Extras Development not included in drafting - Not Committed
24.1 | In attendance report need total check in & total check out counting | New Requirement | Un review
24.2 | In attendance report need total seconday + total primary order count & value | COMPLETED | Un review
24.3 | In attendance report some names not showing - this is error from LNV | COMPLETED | error
24.4 | In all index page date formats should be DD-MM-YYYY and created by user name required fields at each level In all index pages last in at first page required and row count is till 200 numbers. | COMPLETED |  |  | Nihal
24.5 | Also not able to show the total of counting at Many places. | Issue/error
24.6 | Check all indexes while exporting all fields are not coming some are coming blank | Issue/error | completed | omkar
24.7 | on Dashboard primary and secondary order value coming from last month only not before that | Issue/error
24.8 | Secondary order list is not showing in many staff I'd | Issue/error
24.9 | Primary order create option and primary order list shown to all staff | phase 4
25 | IP address SSL certificate 119.18. | phase 4
25.1 | Voucher created by Distributor opening stock, showing to all Distributors | Issue/error |  | omkar
25.2 | While authorised retailer after submit still shows unauthorised In retailer | Issue/error |  |  | Anish
25.3 | ON web distributors all export options give index also and report also - Master | Genuine Requirement |  |  | Nihal
25.4 | Distributor can not convert primary order to so | COMPLETED |  |  | Anish
25.4 | Distributor and staff can not delete anything from anywhere they can just edit details untill next step convert | New Requirement |  |  | Anish
25.4 | Show by module to all in mobile and web | not possible
25.4 | Also email I'd edit option after email verification | New Requirement |  | Sahil | Anish | 2024-05-06 | 2024-05-06
25 | TASK
25.4.1 | Remove Compulsion for email | New Requirement |  | Sahil | Anish | 2024-06-13 | 2024-06-13 |  |  | 2024-06-13 | 2024-06-13 |  | Completed | pending
25.4.2 | staff,retailer,distributor, supplier | New Requirement |  | Sahil | Anish | 2024-06-14 | 2024-06-14 |  |  | 2024-06-14 | 2024-06-14
25.4.3 | Email change from LNV to Neelam Security Issue Security Issue | Issue/error |  | Sahil |  | 2024-06-19 | 2024-06-20 |  | Parin Issues
25 | ISSUES
25.4.3 | Can't able to verify unverified email | Issue/error |  | Sahil | Anish | 2024-06-15 | 2024-06-15 |  | completed | 2024-06-15 | 2024-06-15 |  | completed
25.5 | Sales expenses mobile app | Issue/error |  | omkar | Anish
25.6 | Chrome notification | phase 4
25.7 | Download image option product of month | New Requirement | mobile app | done
26.1.1 | New approved changes in email in email | Issue/error |  | Sahil | Anish | 2024-06-14 | 2024-06-14
26.1.2 | Apply Loading In all module | Issue/error | Web
26.1.3 | Sleep Time logout in web Automatic logout function | COMPLETED | Web | Nihal | [5 empty] | 2024-07-12 | 2024-07-12 |  | COMPLETED | COMPLETED
26.1.4 | Distributor invoice upload | COMPLETED |  | Omkar | Nihal | 2024-07-11 | 2024-07-12 |  | COMPLETED | 2024-07-15 | 2024-07-15 |  | COMPLETED | COMPLETED
26.1.5 | Transport Module | IN PROCESS |  | Chitaranjan | Nihal | 2024-07-27 | 2024-07-27 |  | COMPLETED
32 | Extra Point of phase 4 covered in phase 3
32 | VOUCHER MODULE/New Requirement
32.1 | Voucher in Sales | New Requirement |  | Sahil | Anish | 2024-06-27 | 2024-06-27 |  | COMPLETED | 2024-07-01 | Not Sure |  | IN PROCESS | Pending
32.2 | Voucher CRUD | New Requirement |  | Sahil | Anish | 2024-06-27 | 2024-06-27 |  | COMPLETED | Not Started |  |  |  | Pending
32.3 | Voucher In Sales Return/DC | IN PROCESS |  | Sahil | Anish | 2024-07-01 | 2024-07-06 |  | COMPLETED | 2024-07-06 | 2024-07-06 |  | IN PROCESS | Pending
32.4 | Voucher in Purchase order | IN PROCESS |  | Sahil | Anish | 2024-07-03 | 2024-07-03 |  | COMPLETED | 2024-07-06 | 2024-07-06 |  |  | Pending
32.5 | Voucher SDN | IN PROCESS |  | Sahil | Anish | 2024-07-03 | 2024-07-03 |  | COMPLETED | 2024-07-06 | 2024-07-06 |  |  | Pending
32.6 | Voucher MRN | IN PROCESS |  | Sahil | Anish | 2024-07-03 | 2024-07-03 |  | COMPLETED | 2024-07-06 | 2024-07-06 |  |  | Pending
32.7 | Voucher in Purchase | IN PROCESS |  | Omkar | Nihal | 2024-07-20 | 2024-07-20 |  | COMPLETED | 2024-07-20 | 2024-07-20 |  | IN PROCESS | Pending
32.8 | Voucher in Purchase Return | IN PROCESS |  | Omkar | Nihal | 2024-07-20 | 2024-07-20 |  | COMPLETED | 2024-07-20 | 2024-07-20 |  | IN PROCESS | Pending
32.9 | Voucher in Sales Order | IN PROCESS |  | Omkar | Nihal | 2024-07-20 | 2024-07-20 |  | COMPLETED | 2024-07-20 | 2024-07-20 |  | IN PROCESS | Pending
30 | ISSUES IN WEB
30.1 | product Issue Solving | COMPLETED |  | Omkar/Sahil |  | 2024-06-20 | 2024-06-20 |  | COMPLETED
30.2 | Secondary Order Export (Trade name + Distributor) | COMPLETED |  | Omkar |  | 2024-06-20 | 2024-06-20 |  | COMPLETED
30.3 | PO Exports fields not fetching | COMPLETED |  | Omkar |  | 2024-06-20 | 2024-06-20 |  | COMPLETED
30.4 | Password Save Issue | COMPLETED |  | Omkar |  | 2024-06-20 | 2024-06-20 |  | COMPLETED
30.5 | Purchase Return Issue | COMPLETED |  | Sahil |  | 2024-06-24 | 2024-06-24 |  | COMPLETED |  |  |  |  | COMPLETED
31 | COMMON ISSUES IN MODULES
31.1 | In Each Module Created by, Updated by, Date Format |  |  | Omkar | Anish | 2024-06-19 | 2024-06-19 |  | COMPLETED |  |  |  | COMPLETED | COMPLETED
31.1 | Updated By Date/Time |  |  | omkar | Anish | 2024-06-24 | 2024-06-26 |  | COMPLETED | 2024-06-26 | 2024-06-27 |  | COMPLETED | COMPLETED

## meeting issues 26th
Neelam Pending issue after meeting
Please remember the following text: "Last modified date."(Excel warehouse)
Searching added(warehouse excel)
Fix the pagination issue on the Entries page."
Invoice (Image should not uploaded) Invoice distributor (permission)
Retailer Supplier Distributor supplier (PFC) Fields fetch
According to PFC fields should be field
Tax type gst should be filled from gst fetch | Chittu | Backend
Temp retailer GSt fetch and created date and time
Jobsheet voucher Automatic (outward)
Jobsheet (system date)Outward
Jobsheet supply type doc number current doc date
Jobhseet calculation
Delivery from mmm Delivery to
Neelam and supply
Transporter id and gst name (GST get from API)(Asked for master but chitu said api from gst ) | Chittu | Backend
Vehicle Type remove intransit | Chittu | Backend
BOM calculation (QTY KG ,QTY PCS)
Side bar (BOM ,SET BAR CODE ,PRODUCT BAR CODE ,MASTER CARTOON,PRINT PRODUCT CODE ,SET BAR CODE KA PRINT ,PRINT MASTER CARTON
GALA= USER
Full staff to everyone to asset request
Supplier name should be taken from asset and invoice number and invoice date attach insurance provider name insurance policy number start date and end date of the insurance policy number, warranty expire date,handover date,serial number
Assign to staff Pending serial no index Asset name asset serial number warranty insurance type.
Distributor outward Multiples items
Neelam address in invoice print should be dyanumc print
Supplier master terms of payment fetch in PO.
PO select supplier auto fetch billing address.
Product of the month name change.

## Prints & Reports
No | MASTER MODULE | Developer Status | Task Name | Backend Developer | FrontEnd Developer | Start Date | End Date | Total Days | Backend Status | Start Date | End Date | Total Days | Frontend Status | Test Status
1 | [5 empty] | BACKEND |  |  |  | FRONTEND
1 | Purchase Order | Frontend Only | Print part | NA | Nihal | 2024-07-08 | 2024-07-09 |  | COMPLETED
2 | Retailer/Distributor Pending Sales Order Report | IN PROCESS | Report Format | Omkar | Nihal |  |  |  | IN PROCESS |  |  |  | IN PROCESS
3 | Warehouse Stock Report | IN PROCESS | Report Format | Omkar | Nihal | 2024-07-17 | 2024-07-24 |  | IN PROCESS | 2024-07-15 | 2024-07-24 |  | IN PROCESS | Pending
3.1 | Invoice upload Distributor | IN PROCESS |  | Omkar |  | 2024-07-23 | 2024-07-23 |  | COMPLETED | 2024-07-18 | 2024-07-18 |  | COMPLETED
4 | Sales E-invoice Print | Not Started |  | Chitaranjan | Nihal
5 | Delivery Note print | Not Started |  | Chitaranjan | Nihal